This WP deals with the definition of the spatial-temporal scale of the LLs in both theoretical and empirical

terms. For such a task, the work will take advantage of the transdisciplinary nature of the team, bringing

together multidisciplinary and participatory co-design approaches in cooperation with local living labs.

Starting from defining the territorial scale for assessing Living Labs within their context and analyzing the

context, a flexible methodology to select and engage the actors will be proposed, allowing the

co-development of transition pathways to scale and amplify agroecology to the whole territory. This will

provide the necessary context to critically assess the current state of the agri-food system in each LL

region, identify the scale, and challenges, and finally co-design potential pathways to scale agroecology

within the territorial level. This WP will feed task 7.3 of the Partnership (identifying and engaging actors

and stakeholders of the value chain).

Task 1.1. Scale and context of the agroecological transition, M1- M12 (LEAD: CSIC-JLVV): Activities

will start by identifying the territory with the geographic area (e.g., NUTS 2, 3), continuing with the

co-definition of the territorial boundaries with the actors of the LLs and current analysis of the state of the

agri-food system in both, supply and demand. This will be done through a combination of existing

concepts, tools, and models such as ZALF’s foodshed model (MFSS model) (Zasada et al. 2019) and

participatory mapping using interactive tools with farm scale living lab actors (Walthall et al. 2022). This

will be made in close coordination with task 2.1.

Task 1.2. Pathways to scale the AE living lab to a territorial scale (O1.3), M4-36 (LEAD: CREA-CC):

Based on the results of the previous task, a step-by-step procedure for the identification and engagement

of stakeholders and actors to upscale the agroecology living labs to a territorial scale (i.e. ALAS- López

García et al. 2021) will be designed. The task will contribute to co-designing potential pathways to scaling

out, deep (WP2), and up (WP5) agroecology through TAELabs (Moore et al, 2015).

This WP will build on the first results in WP1 on the spatial-temporal context of the LLs and will provide

the framework and methods to quickly convert the existing multi-actor initiatives into territorial

agroecology living labs (TAELabs) and to operationalise the collaborative actions within the LLs. The WP

will function as the central connection node for the praxis-oriented WPs (mainly WP3, WP4, and WP5),

where concrete and practical actions will occur, e.g., co-developing and co-experimenting solutions to

problems identified by local participants. The process design is based on iterative loops of

problem-framing and problem-solving connected to all these WPs, including WP1. The workflow will be

based on transdisciplinary knowledge co-production theories (Lang et al. 2012, Rogga et al. 2018). In the

framework, key elements of LLs and TAELabs will be considered: 1) long-term orientation to

agroecological transition, 2) transdisciplinary research approach with co-design and co-development of

solutions, 3) creating space for joint experimentation, co-learning, and networking, as well as 4)

participatory monitoring, evaluation, and reflexivity (cf. Schäpke et al. 2018, Hossain 2019, Mc Phee et

al. 2021). The conceptualisation includes the performance areas of LLs proposed by Bouwrna et al.

(2021): set-up, interactions, actions, innovation, products/services, reputation, outcomes/impacts; and

identifies concrete actions for each of these areas and TAELabs (e.g., jointly developing a theory of

change). Drawing on assemblage theory (Latour 2013), this WP aims to bridge issues and processes at

different scales of observation, by focusing on the socio-ecological features of each territory as mediators

between the agroecosystems and the specific transition pathways and outcomes they generate. Through

this WP, LL participants and the local social fabrics in which they are embedded, including the farmer

organisations, will be strengthened, as they will gather evidence and skills for improving local agri-food

governance ecosystems. Also, this WP will connect with WP5, specifically with task 5.3 providing a

cross-comparison of outcomes that will be disseminated at a European and policy-making level, and will

also interact with Tasks 7.3 and 7.4 of the European Agroecology Partnership.

Task 2.1. Co-design of the methods and tools to implement TAELabs, (M1-M36), (Lead: ZALF-MB,

Co-lead CREA-CC). This transversal task aims at jointly developing the ethical principles of the TAELabs

(including role perceptions), the transdisciplinary collaboration, concepts for the co-design processes,

and methods to be applied (e.g. participatory methods, citizen science) in both creating new TAELabs or

supporting the strengthening and scaling of ongoing ones. This includes also establishing the position of the “agroecology living lab facilitator” (TAELabs facilitators) in each TAELabs as an intermediate person

between the project and the TAELabs, and between the TAELabs actors (farmers, citizens, scientists,

policy-makers), supporting the application of the methods and co-development of the processes (e.g.

see previous projects where a similar figure was already proposed, such as FoodSHIFT2030, FInAL).

Task 2.2 Co-assessment, monitoring, and reflection of the TAELabs performance and the

evaluation of their outcomes, (M1-M36), (Lead: CSIC-PB, Co-lead: ZALF - MB). This task will

co-develop an assessment framework that covers all dimensions of transition experiments (inputs,

processes, outputs, outcomes) (Luederitz et al. 2017) as well as the above-mentioned LL performance

areas and influence spheres (Bouwrna et al. 2021). Thus, the framework enables 1) reflecting the needs

and “internal functioning” of the LL by assessing the input and processes and 2) assessing the

contribution of the outputs from the TAELabs (mainly outcomes from WP3 and 4, but also considering

results from WP1 and WP 5) to the agroecological transition. This task will set a framework to measure

such societal impacts in the long term that will specify WHAT, WHY, WHO, WHEN, and HOW the

assessment will be carried out in terms of methods and criteria. Generally, TAELabs facilitators and

actors will be actively involved in developing the framework and conducting the assessment itself,

following co-evaluation principles (Schaefer et al 2021).

Task 2.3. Co-dissemination of the LL results, (M6-36), (Lead: CSIC-DL). This task will set up a

working group with regular online meetings between the task lead and all TAELabs facilitators to

coordinate activities and information flows between the different tasks (in WPs 2, 3, 4, and 5) to be

performed in each TAELabs. It will coordinate how deliverables produced are disseminated in each LL

territory, with adapted tools for all target actors’ groups, to feed knowledge co-production iterative cycles

within each LL and between WPs. A Local Communication Plan will be outlined for implementation in

each TAELabs, identifying essential tools and storylines. However, methods for local co-dissemination of

results may vary among sites and even within the project’s evolution and should be in local languages.

Dissemination will be used in the local contexts common communication tools, such as social media and

websites, and also making use of audiovisuals to broadcast video stories on agroecological practices on

farms, territories or linked to commercial dynamics, as well as on events relevant to the project. The

TAELabs actors will be asked to contribute with their own social media and audiovisuals to collect

different viewpoints on common topics and challenges.

This WP includes assessments of ecological and biophysical factors across farm and landscape scales,

together with assessments of perceptions living lab actors have related to their landscape. The central

aim is to identify the most suitable farming practices to promote landscape-scale agroecological

transitions using a participatory selection process that includes three steps: visioning, mapping, and

assessments of landscape management. The in-depth visioning process will take place within the LLs

charting a course and providing valuable insight into the LL challenges. Mapping will engage a wider

range of actors within the territory to create multi-perspective agroecosystem visualisations of goals and

challenges. The participatory assessment will build on the first two steps, once again engaging LL

stakeholders to create an actionable pathway between farm practices and the territory.

Task 3.1 Visioning exercises with each TAELab, M6-12, (LEAD: ZALF-MB). Conduct semi-structured

interviews and then focus groups with key local stakeholders to elucidate which values, roles, and

practices can form pathways toward individual (relational) agroecological landscape visions. The

interviews will employ a three-horizon framework and the issues and desires outlined in the interviews

will be discussion points at the beginning of the project as a means to co-identify challenges faced by

each AELL. Commonalities and ambitions among the LLs will be collected and participatory activities

such as ‘Walking interviews’ or ‘photovoice’, to develop a rich picture will be implemented to capture

landscape values, biodiversity knowledge, and expectations on the AE transition.

Task 3.2. Mapping of existing agroecosystem and challenge definition, M6-18, (LEAD: AU-TS). LL

actors will be engaged using participatory research methods to map current farming systems and

landscape/territory scale management practices, as well as goals and challenges. Following the territory

definition adopted in WP1 and the visions in 2.1, a broad and diverse group of local actors will be

engaged within the geography to create a series of maps of the agri-food system using innovative

participatory mapping methods (online and/or in-person). The maps will become visualizations

highlighting a broad range of perspectives and directionalities (current, aspirational) for the territory.

Task 3.3. Participatory assessment of landscape management in the territory surrounding LLs,,

M12-24, (LEAD: CSIC-JLVV). An existing self-assessment and self-monitoring tools (e.g. Farm-level

Agroecology Criteria Tool, F-ACT) will be applied with LLs focusing on the first three levels of

agroecological transitions (Gliessman 2016). A set of potential practices to be co-implemented to

advance in the AE transition at the territorial scale (Gliessman’s levels 4 and 5) will be explored

highlighting landscape elements for re-designing the agroecosystem, in cooperation with consumers and

trends in consumer demands. Such proposals will inform farmers’ choices in landscape management to

improve their ecological performance. Adoption of the innovative farming practices proposed will be

strengthened by marketing, delivery, and producer-consumer cooperation strategies co-designed in tasks

4.1 and 4.2.

WP4 is a core empirical work package assessing the socioeconomic sustainability of agroecological

transitions. In WP4 we take a high-risk - high gain approach (see risk mitigation below) in pushing

theoretical frontiers of how to better consider the role of non-human actors in the decision making and

analysis of agroecological transitions. To avoid a dichotomous perspective of production and

consumption, WP4 draws on assemblage theory to elevate and operationalise the more-than-human

aspects of agroecological landscapes and supply chains. Working at a landscape level, three tasks are

designed to assess socioeconomic variability at three layers of the local food value chains, that will

overlap in time to implement joint assemblage assessment: 1) place-based farming and marketing,

collective strategies, 2) across supply chains, and 3) their policy coherence. Our approach will pay

attention to the unique interplay between policy and infrastructure configurations and subjective

materialities in each Living Lab, thus avoiding a one-size-fits-all approach to agroecological transitions

(Lea at al. 2022). We will develop a conceptual approach with 3 steps: 1) Developing a ‘toolbox’, 2)

analysis including non-human actors, and 3) synthesis/theory-building. The fieldwork will be performed in

depth in the LLs of Södertälje, Brandenburg, and Madrid, but its outcomes will also be discussed in the

LLs of Bornholm and Rome. WP4 outcomes aim at improving the socio-ecological and economic

performance of local value chains, logistics, and delivery networks in all LLs involved, as well as

producing proposals for improving policies and governance frameworks for the multidimensional

sustainability of agroecology-oriented value chains. Its cross-case learnings will feed into WP5 with

insights for useful methods and indicators to monitor the AE transition from a trans-scalar perspective,

linking the local and the European scales.

Task 4.1. Business models & collective and self-organizational dimensions for AE transition

(M6-36), (LEAD: CSIC-DL). This task will explore how the interlinkages between farmers’ socio-economic

profiles, marketing strategies (including multi-product, collective, and hybrid producer-consumer forms),

and biophysical and institutional features of each territory, shape different forms of business models, and

forms of farmers’ self-organization bodies for local marketing and delivery applying an agroecological

approach (López-García and Carrascosa-García 2024). Assemblage thinking will be used in farmers'

groups’ self assessments, through interviews and participatory workshops led by the living lab facilitators.

It will focus on non-human actors (such as the machinery used, or landscape elements) -and the

conditions they pose on the self-organization forms self-assessed by farmers and their interlinkages with

non-agricultural actors (consumers, NGOs, Local Authorities). T4.1 will provide insights on the suitable

territorial scale to understand more-than-human assemblages to improve (fringe) the socio-ecological

and economic sustainability of the local value chain. Task 4.2. Landscapes and foodscapes: assemblages between food production and circulation,

socio-economic actors and territories (M6-36) (LEAD: SU-JH, Co-lead ZALF-MK). This task will

assess the socioeconomic sustainability of agroecological value chains by re-conceptualizing and

operationalising value chains as assemblages, with the intent that hitherto ‘invisible’ aspects such as

storage and transportation are given explicit agency and co-benefits of agroecological farming

(biodiversity, increase soil carbon) are made visible. From M6-12 a toolbox for operationalising value

chain assemblages will be co-developed with partners in two LL (Sweden and Germany). This toolbox

will focus on assessing enabling and constraining factors to enact agroecological transitions (following

Gidden’s structuration theory) for each actor (including more-than-human actors such as contracts and

infrastructure). In M12, the toolbox will be implemented with 3 LLs partners on enabling and constraining

factors, which can help feed into task 4.3 on policy coherence. This will deliver improved performance for

the local value chains, optimizing and reducing costs and impacts and thus improving prices for

producers and consumers, while also improving environmental performance by making agroecological

practices economically viable. In M24 case study analysis and synthesis, work will reflect on the

operationalization process in a methodological scientific paper as well as a reflection from the TAELabs

project to disseminate a toolbox for wider use.

Task 4.3. Policies, territories, and people: multi-level assessment of policy coherence, (M15-27)

(LEAD: CSIC-SC). This task will assess the coherence of (multi-level) policies for agroecological

transitions (eg. at municipal, regional, national, and EU levels). Coherence can be understood as

convergence in goals and outcomes of policy processes across policy domains (horizontal) or policy

levels (vertical) (Nilsson et al. 2012; Sandstrom et al. 2022). Coherence is, in turn, influenced by

discursive frames (or beliefs), institutional arrangements, and political factors (the interplay between

interests and power in policymaking). We will apply assemblage thinking to achieve a territorialised

understanding of how actors co-produce policy arrangements and their outcomes from a

lived-experience perspective, the places in which interaction and negotiation occur, and the non-human

elements present in these contexts and in policy implementation. Coherence analysis usually involves

three steps (Nilsson et al. 2012; Nilsson et al. 2019): (1) An inventory of objectives and instruments in

key policy domains (levels), supported by document review and validated by actors and other “experts”;

(2) Participatory workshops to co-create a screening matrix characterising the direction, intensity, and

pattern of interactions across goals and/or instruments in different domains or policy levels; and (3)

in-depth analysis of specific interactions (in-coherences) selected in the previous step. This step will

involve literature reviews, interviews, participant observation, and methodologies for systems thinking

and scenario co-creation.

The WP builds on TAEL actors’ proficiencies and expectations to stimulate newly designed policy

measures and AKIS interventions that may enable and accelerate the agroecological transition at

different territorial scales. WP5 will specifically foster exchanges within and across the project’s living

labs to stimulate actionable knowledge in the areas of policy-making and competence development,

fostering coordination to promote local innovation while aligning with broader national and EU goals.

Task 5.1. Capacity development on territorialized agroecological policies (M15-35) (Lead:

CSIC-SC). Based on T3.4 outcomes and indications, interactive workshops in each LL will be organised

to allow familiarisation and learning on agroecologically-oriented policies and to categorise territorially

relevant policy interventions. The workshops will enhance active actors’ engagement in institutional

dialogue and lead to the setting up of a ‘Community of Policies - CoP’ aimed at exchanging experiences

and strengthening territorialised agroecological approaches. A common template will facilitate the

identification of enabling policies for transition, gaps, and needs, to be shared within the CoP and with

the broader agroecological community to nurture possible policy interventions at both EU and local

scales. A policy brief will outline emerging policy initiatives fostering agroecological territories as well as

plausible pathways to co-determine genuine agroecological policies.

Task 5.2. Exploration of AKIS potential for agroecological socio-technical environments (M15-35)

(Lead: FIRAB-LC). AKIS is becoming increasingly important in the EU, but it is constrained by a still

limited familiarity among practitioners and an inefficient integration of its components, particularly in

agroecology for which training and advisory remain largely unaddressed. A factsheet focused on

agroecology-territorial AKIS as well as examples and models in Europe will allow a greater

alphabetisation of LL participants and stakeholders on its potential to accelerate the transition.

Furthermore, LL workshops will be carried out to capitalize outputs from WPs 2 and 3 and build concrete

opportunities for training (including P2P learning) and co-innovation (e.g. developing proposals for

EIP-AGRI Operational Groups or LEADER’s Local Action Groups) which may ultimately build the

TAELabs legacy.

Task 5.3. Innovative governance for territorial agroecological living labs and interface with

European initiatives (M15-35), (Lead: AU-TS). This task involves developing a framework for innovative

and coherent governance strategies (bridging place-based to EU scales) to support transformative

change toward agroecology with landscape/territory scale living labs. The elaboration of innovative

governance strategies will draw on mutual learning across the 5 TAELabs Living Labs, synthesizing

outputs across work packages and building on the findings of tasks 2.1, 4.3, 5.1, and 5.2. This will

culminate in a joint symposium involving participants in other initiatives and projects across Europe. We

will employ a system approach to conduct a meta-level analysis of outcomes, considering the scalability

potential of both governance processes and more tangible LL results. The outcomes will feed into the

Agroecology Partnership and other European and national projects (e.g., Leguminose) showcasing evidence-supported practice and learning points on aspects of institutional engagement and

agroecological territorial governance. The governance innovation framework will support the definition of

an agenda for the territorial development of AE. Moreover, benefiting from direct partners' connections,

TAELabs will build on key Agroecology Partnership methodologies and tools to strengthen LLs

functioning and provide feedback on their effectiveness.

Task 6.1 Project administration (LEAD: CSIC, M01-36). In month 3 it will be published a Project

Handbook for partners (D6.1) to ensure optimal participation and coordination, including specifications on

KPIs, and finetuning of roles, communication, and decision-making protocols between WP, task leads

and co-leads, and LL facilitators. Such a Handbook will be interlinked to a Transdisciplinary Roadmap

(M6.1) to coordinate fieldwork, cross-case work, and dissemination activities among partners and living

labs, and to D2.1, D6.2, D6.3, and D6.4. All of them will be elaborated throughout a participatory process

among all partners. The Consortium will have a yearly physical plenary meeting with representatives of

all partners, to take formal decisions and implement strategic planning and evaluation of intermediate

outcomes, based on KPIs. The project coordinator and WP leads will join a Management Board to meet

online every two months, including task leaders and LLs facilitators when necessary. Each Task leader will coordinate with the group of LL facilitators the activities to be performed in each LL Periodic dialogue

with WP and Task leads from Agroecology Partnership’s WP7, through TAELabs’ Task 5.3, will improve

guidance of the project in the framework of Agroecology Partnership.

Task 6.2 Communication, Dissemination and Exploitation Plan management (LEAD: CSIC-DL,

M01-36). The project will implement general Communication and Dissemination (CD) tools such as a

dedicated website, press releases, and Social Media activities. It will ensure the publication of both

scientific, peer-reviewed publications and dissemination resources, and attendance to dedicated,

international conferences and congresses. Finally, tasks 2.3, 5.1, 5.2, and 5.3 will include dissemination

and knowledge co-production activities at local scales and linking the LLs with other processes and

projects at the European scale. All these actions are further described in Annex VII. A Communication,

Dissemination and Exploitation Plan (D6.2) will be set up at the beginning of the project and regularly

updated as a living document, including specific KPIs, to coordinate all CD activities at both Consortium

and LL scales.

Task 6.3 Risk management and maximizing impacts (LEAD: CSIC-DL, M01-36). A detailed list of

expected risks and related risk mitigation measures regarding each WP has been shown in the previous

pages. Based on such a list and the defined general KPIs, a ‘Strategic Impact Optimisation and Risk

Management Plan’ (D6.3) will be approved at the beginning of the project. It will include a risk register, to

be updated throughout the project; monitoring initiatives of a set of activities and interactions with the

various target groups of the LLs (farmers, processors, retailers, consumers, Local Authorities, and Local

NGOs), and on wider scales (Operational Groups, Local Action Groups, national-wide AKIS, Agroecology

Partnership, etc.); activities to maximize transferability and impacts for policy-makers at different scales;

or monitoring transfer and adoption of results and formulating recommendations to improve uptake

capacity. Such a plan will set protocols to monitor the project’s impacts and to suggest actions to further

maximize impacts and introduce strategic management. The Management Board will assess and validate

consortium targets at least twice over the project lifetime and will adjust the project direction and

organization when necessary. WP Leaders will present an assessment of progress and risks at the yearly

Consortium meetings.

Task 6.4 Data management plan (LEAD: CSIC, M01-36). CSIC will lead the setup, approval, and

maintenance of a Data Management Plan (DMP), which is to evolve along the project’s lifetime, and to

implement the policy for publication of data. The application of comprehensive self-assessments will

validate the adherence to FAIR principles within the project and formulate specific suggestions to

improve the data management practice. Adherence to ethical protocols and the protection of the privacy

of partners and participants will be ensured. All research data resulting from the project will be made

available as soon as possible after the consortium has analyzed them and published their findings. The

project will comply with Horizon Europe criteria for Open Access to publications and research data and

related obligations, through the institutional Open Access repository of the Spanish National Research

Council, DIGITAL.CSIC.