TAELabs Data Management Plan

D 6.4

WORK PACKAGE 6, TASK 6.4.

DELIVERY DATE: 19-02-2026

Deliverable version: v0.1

Dissemination level: Consortium internal

Authors: Michela Pirredda and Daniel López-García

| DOCUMENT INFORMATION |  |
| --- | --- |
| Project Acronym | TAELabs |
| Project Title | Territorial Agroecological Living Labs |
| Project Leader | Dr. Daniel López-García |
| Project Coordinators | Dr. Daniel López-García and Dr. Michela Pirredda |
| Project Duration | 36 Months ( 15/05/2025 to 14/05/2028 ) |
| Deliverable Number | D 6.4 |
| Dissemination Level | Consortium Internal |
| Contractual Delivery Date | August 2025 |
| Delivery Date | February 2026 |
| Version | v0.1 |
| Pages | 23 |
| Work Package | WP6 |
| Lead Beneficiary | CSIC |
| Keywords | Data access-sharing-preservation, ethics policies, FAIR data, metadata, TAELabs Data Management Plan (DPM). |

| DOCUMENT HISTORY |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date | Version | Authors | Reviewers | Description |
| 19-02-2026 | v0.1 | Michela Pirredda and Daniel López-García | TAELabs consortium members | This document provides an overview of the TAELabs project data management plan. |

| Table of contents: |  |
| --- | --- |
| Chapter 1: Data Management Plan overview | P. 5 |
| Chapter 2: Administrative details | P. 6 |
| Chapter 3: Data summary | P. 8 |
| Chapter 4: Data information | P. 9 |
| Chapter 5: Data overview/infrastructure | P. 11 |

| Tables: |  |
| --- | --- |
| Table1: TAELabs project administrative details | P.6 |
| Table 2: TAELabs data summary | P. 8 |
| Table 3: General information about TAELabs research tasks | P. 11 |
| Table 4: Data used/gathered during the research mission period | P. 20 |
| Table 5: TAELabs attachment concerning basics / Organizational aspects for data handling | P. 23 |

Executive summary:

This document marks the 6.4 deliverable of the TAELabs project. The current Data Management Plan aims to provide a comprehensive overview of all the data collected, stored, analysed, exchanged and preserved within the project.

| List of abbreviation: |  |
| --- | --- |
| Term | Description |
| DMP | Data Management Plan |
| FAIR | Findable, Accessible, Interoperable, and Reusable |
| GDPR | General Data Protection Regulation |
| IPR | Intellectual Property Rights |
| N/A | not applicable |
| TAELabs | Territorial agroecological living labs |

1. Data Management Plan (DPM) overview

The Data Management Plan (DMP) is a formal document that contains comprehensive information about the data generated or managed during and after a research activity within a given project. It covers everything from the collection and storage of the data to its analysis, sharing and preservation. As a 'living document', it should be updated throughout the project to ensure the data is well managed, secure and reusable. DMPs help researchers to address key issues early on, saving time and preventing potential problems.

Data agreements are contracts that govern the transfer and use of data between parties. They outline which data is shared, how it can be used and the security requirements for handling it. They may include stipulations regarding confidentiality, usage restrictions and data handling, as well as the period for which the data is available. This helps to prevent data misuse and ensure compliance.

To this end, our management plan and data agreements address several key questions and provide a clear framework for doing so. They should be coherent with the national regulations of the Consortium members' countries.

2. Administrative details

Table 1: TAELabs project administrative details.

| Name of the consortium | “TAELabs” Territorial Agroecological Living Labs |
| --- | --- |
| Duration | 15.05.2025 – 14.05.2028 |
| Project leader / PI | Daniel López García Contact: daniel.lopez@cchs.csic.es |
| Project coordinators | Daniel López García Contact: daniel.lopez@cchs.csic.es Michela Pirredda Contact: michela.pirredda@cchs.csic.es |
| Consortium partners (corresponding researchers) | Corrado Ciaccia (CREA, Italy) Daniel López (IEGD-CSIC, Spain) Jamila Haider (SU-SRC, Sweden) Luca Colombo (FIRAB, Italy Maria Busse (ZALF, Germany Rebecka Milestad (KTH-SEED, Sweden) Tiffanie Stone (AU-Agroecology, Denmark) |
| Research program | TAELabs 1st co-funded call Agroecology Partnership (from here only TAELabs) |
| Data manager of the consortium | Daniel López Contact: daniel.lopez@cchs.csic.es Michela Pirredda Contact: michela.pirredda@cchs.csic.es |
| Contact for data supply / data delivery | Contact person(s) of the Work Packages (WPs) WP1 Setting the framework for stakeholder engagement: Corrado Ciaccia (CREA, Italy) corrado.ciaccia@crea.gov.it. WP2 TAELabs design and their contribution to the accelerated AE transition Contributors: Maria Busse (ZALF, Germany) Maria.Busse@zalf.de and Alma Moroder (ZALF, Germany) Alma-Maria.Moroder@zalf.de WP3 Re-designing agroecosystems landscapes: Tiffanie Stone (AU-Agroecology, Denmark) tstone@agro.au.dk WP4 Re-assembling territorial agroecological value chains: Jamila Haider (SU-SRC, Sweden) jamila.haide@su.se and Courtney Adamson (SU-SRC, Sweden) cjada@kth.se. WP5 Policies and AKIS as enablers for agroecological transitions: Luca Colombo (FIRAB, Italy) l.colombo@firab.it. WP6 Coordination and Management: Daniel López (IEGD-CSIC, Spain) daniel.lopez@cchs.csic.es and Michela Pirredda (IEGD-CSIC, Spain) michela.pirredda@cchs.csic.es |
| Project Description | The TAELabs is an international European project aims to identify models and co-design agroecological solutions, by actively involving local stakeholders, such as farmers, public bodies, non-governmental organisations and consumers. Five living laboratories will be established across different countries and territories to achieve this: two in metropolitan areas (Madrid, Spain and Rome, Italy); two in rural areas (East Brandenburg, Germany and Bornholm, Denmark); and one in a peri-urban area (Sörmland, Sweden). The project is based on three pillars: the ecological and biophysical aspects; the socioeconomic aspects; and collaborative food governance and policies. The project aims to co-design and co-create solutions that promote the agroecological transition while respecting the needs and diversity of different areas, territories and countries. This will be achieved through an 'assemblage' approach and a cross-cutting, transdisciplinary methodology at every stage of development. This will create models that can be adapted to different situations and implemented across Europe. |
| Relevant guidelines for handling research data | - Regulation (EU) 2016/679 (GDPR) – acknowledged as reference framework, although no personal data are collected or processed in the project. - Horizon Europe Programme – Model Grant Agreement (Open Science, Research Data Management and Ethics provisions). - Horizon Europe Programme Guide and related guidance on Open Research Data. - FAIR Data Principles (Findable, Accessible, Interoperable, Reusable). - Guidelines for responsible research and innovation (RRI) and participatory research in living labs. - Institutional guidelines of project partners on data management, ethics and intellectual property. |
| Date of First Version | Version 1 from 19/02/2026 |
| Date of Last Update | Version 1 from 19/02/2026 |

3. Data summary

Data management will be carried out under WP6, Task 6.4: Data Management Plan (DMP).

The DMP will support the project's scientific objectives and disseminate its results. The TAELabs project will use data from previous publicly available research and the current state of openly accessible sources. The data generated or reused will come from scientific studies. In addition, TAElabs will generate several datasets, which will be reused to meet the project objectives.

Research data will be in traditional file formats such as .xlsx, .docx, .pdf and .jpg. A more detailed description of the data is provided in Table 2 (Data Summary); which will be updated throughout the project, particularly with regard to public research data, which will be subdivided according to format and purpose. The DMP also provides some initial details on the treatment of public and confidential research data.

Table 2: TAELabs data summary.

| Data | Format | Description |
| --- | --- | --- |
| Public and Confidential Research Data | .doc, .docx, .pdf, .xls *.csv | This includes non-confidential data required to validate the results presented in scientific publications, as well as non-confidential research products created or used within the TAELabs project framework. This includes any form of data and research products (including designs, datasets and code) that were created or used within the project framework and are considered confidential according to the TAELabs IPR protection policy. |
| Project deliverables | .doc, .docx, .pdf | Confidential and public deliverables listed in the Grant Agreement. |
| Promotional materials and templates | .psd (Photoshop), .indd (Indesign), .jpg, .png, .pdf, .ppt/pptx,.doc/docx,.mp4 and similar formats | Leaflets, posters, logos, PowerPoint presentations, videos, templates for presentations and deliverables, etc. |
| Official documents | .pdf | Excel files containing basic personal data (name, surname, organisation, phone and mobile numbers, email address) and .jpg. files containing photographs. |
| Meetings’ data | .pptx, .pdf, .doc/docx and similar formats | Presentations, and any other material discussed or created during project meetings. |

4. Data Information

What types of data will the project generate and collect?

TAELabs will produce a large set of qualitative and quantitative data on the environmental, economic, policy, and social features, performance, and assessments of the Living Labs and the people and organizations involved and related to them. This includes socio-economic data, and data to characterize the local food systems and chains, which will be provided by the local food chain operators, including local farmers. There will be no experimentation with humans or with other non-human beings.

What standards will be used?

CSIC will lead the setup, approval, and maintenance of a DMP in the first six months of the project, to analyse and describe the main elements of the project’s data management policy. The DMP is to evolve along the project’s lifespan and to implement the policy for the publication of data, particularly whenever significant changes arise within the management of the consortium and the generation of datasets. According to the guidelines provided by Horizon Europe, the resulting data must be FAIR: Findable (metadata, unique IDs), Accessible (access rules, repositories), Interoperable (standards), and Reusable (licensing) as much as it is possible, excepting when there are substantial reasons to keep the data confidential. The Principal Investigator (in advance, PI) is responsible for data management and will oversee compliance with FAIR standards.

The DMP will clearly indicate what datasets will be made openly available and shared for verification and reuse and which ones will impose other levels of openness. The application of comprehensive self-assessments will validate the adherence to FAIR principles within the project and formulate specific suggestions to improve the data management practice, at least in the middle and in the end of the project. Adherence to ethical protocols and the protection of the privacy of partners and participants will be ensured. All personal data obtained from interviews, workshops, or other fieldwork will be anonymized.

How will this data be exploited and/or shared/made accessible for verification and reuse?

The Management Board of the project, composed of all WP leaders, will agree and publish the guiding principles for the governance and exploitation of the data generated and the publications derived from it (see project handbook), which will be included in the DMP. All publishable research data resulting from the project will be made available as soon as possible after the consortium has analysed them and published their findings. The Project’s Management Board will indicate what datasets will be made openly available and shared for verification and reuse and which ones will impose other levels of openness. We will ensure open access to all peer-reviewed scientific publications resulting from the project by: (a) depositing a copy of the published version or final peer-reviewed manuscript accepted for publication, whatever the journal policy allows for, in an open repository (i.e. Digital.CSIC); (b) deposition and open access availability of such publications will take place after the embargo periods set by the European Commission; and (c) these items will be accompanied with standardized bibliographic metadata that identify the deposited resource and will also include such metadata.

How will this data be curated and preserved?

The project consortium will provide Open Access to both research data generated during the project once the embargo will be finalised, and for a maximum embargo period of two years after the formal end of the project. This will include data, associated metadata, and tools and instruments necessary to validate the scientific results. Sensitive personal data will not be available to protect confidentiality of the informants. The project will comply with Horizon Europe criteria for Open Access to publications and research data and related obligations, through the institutional Open Access repository of the Spanish National Research Council, DIGITAL.CSIC. DIGITAL.CSIC, created in 2008. DIGITAL.CSIC provides specific support to comply with the Commission’s requirements for open access to publications and data and guarantees long-term storage, easy access, and downloading facilities for open-access data. DIGITAL.CSIC assigns Digital Object Identifiers (DOI) to datasets for their clear identification and citability and fulfils all the quality criteria established by the Re3data directory of repositories. DOIs will be assigned to generated datasets directly by DIGITAL.CSIC through CSIC institutional membership to DataCite once the datasets are uploaded into its platform. The costs of all services provided by DIGITAL.CSIC will be entirely assumed by CSIC.

5. Data overview/ infrastructure

Basics / Organizational aspects for data handling:

- Personal data must always be pseudomysed and encrypted.

- Model (run) data must always be stored with details of the model and with the output parameters.

- The location of datasets must be clearly specified, as well as intention to publish it after finalizing the project in Open Access repositories, specifically DIGITAL CSIC (see its data policy: https://digital.csic.es/dc/politicas/politica-datos-digital-csic.jsp).

Table 3:  General information about TAELabs research tasks.

| WP 1 | Research Task/Analysis name | Task (T)/Topic | Start Date month (M) | End Date month (M) | Principal Investigator (s) | Organizing Institution |
| --- | --- | --- | --- | --- | --- | --- |
| Conceptual framework | Literature Review | T 1.1. Scale and context of the agroecological transition | M2 | M12 | José Luis Vicente Vicente | IEGD-CSIC (Spain) |
| Indicator framework | Individual meetings/ interviews | T 1.1. Scale and context of the agroecological transition | M3 | M6 | José Luis Vicente Vicente | IEGD-CSIC (Spain) |
| Indicator framework | Territorial boundaries of the LL | T 1.1. Scale and context of the agroecological transition | M6 | M11 | José Luis Vicente Vicente | IEGD-CSIC (Spain) |
| Indicator framework | Analysis of the current state of the agri-food system | T 1.1. Scale and context of the agroecological transition | M11 | M12 | José Luis Vicente Vicente | IEGD-CSIC (Spain) |
| Conceptual framework | Literature Review | T 1.2. Pathways to scale the AE living lab to a territorial scale | M2 | M30 | Corrado Ciaccia | CREA (Italy) |
| Indicator framework | Methodology and the handbook for stakeholders’ identification and engagement as actors | T 1.2. Pathways to scale the AE living lab to a territorial scale | M5 | M6 | Corrado Ciaccia | CREA (Italy) |
| Indicator framework | Individual meetings/ interviews | T 1.2. Pathways to scale the AE living lab to a territorial scale | M10 | M30 | Corrado Ciaccia | CREA (Italy) |

| WP 2 | Research Task/Analysis name | Task (T)/Topic | Start Date month (M) | End Date month (M) | Principal Investigator (s) | Organizing Institution |
| --- | --- | --- | --- | --- | --- | --- |
| Conceptual framework | Literature Review | T 2.1. Co-design of the methods and tools to implement TAELabs | M2 | M12 | Maria Busse and Alma Moroder | ZALF (Germany) |
| Indicator framework | Interviews with lab facilitators | T 2.1. Co-design of the methods and tools to implement TAELabs | M2 | M7 | Maria Busse and Alma Moroder | ZALF (Germany) |
| Indicator framework | Webinar on co-creation | T 2.1. Co-design of the methods and tools to implement TAELabs | M5 | M6 | Maria Busse and Alma Moroder | ZALF (Germany) |
| Indicator framework | Discuss expectations, roles and co-design process | T 2.1. Co-design of the methods and tools to implement TAELabs | M5 | M9 | Maria Busse and Alma Moroder | ZALF (Germany) |
| Conceptual framework | Literature Review | T 2.2 Co-assessment, monitoring, and reflection of the TAELabs performance and the evaluation of their outcomes | M1 | M36 | Daniel López | IEGD-CSIC (Spain) |
| Indicator framework | Workshop on drafting the concept of assessment criteria | T 2.2 Co-assessment, monitoring, and reflection of the TAELabs performance and the evaluation of their outcomes | M7 | M15 | Daniel López | IEGD-CSIC (Spain) |
| Indicator framework | What criteria work well within the co-design process and what should be adjusted? | T 2.2 Co-assessment, monitoring, and reflection of the TAELabs performance and the evaluation of their outcomes | M1 | M36 | Daniel López | IEGD-CSIC (Spain) |
| Indicator framework | Co-assessment exercise in a participatory format with lab members | T 2.2 Co-assessment, monitoring, and reflection of the TAELabs performance and the evaluation of their outcomes | M24 | M29 | Daniel López | IEGD-CSIC (Spain) |
| Indicator framework | Compare results / outcome of the co-design process | T 2.2 Co-assessment, monitoring, and reflection of the TAELabs performance and the evaluation of their outcomes | M29 | M32 | Daniel López | IEGD-CSIC (Spain) |
| Conceptual framework | Literature Review | T 2.3. Co-dissemination of the LL results | M9 | M18 | Michela Pirredda | IEGD-CSIC (Spain) |
| Indicator framework | Web page/ Workshop(s)/ seminar(s)/ congress(es) | T 2.3. Co-dissemination of the LL results | M9 | M36 | Michela Pirredda | IEGD-CSIC (Spain) |

| WP 3 | Research Task/Analysis name | Task (T)/Topic | Start Date month (M) | End Date month (M) | Principal Investigator (s) | Organizing Institution |
| --- | --- | --- | --- | --- | --- | --- |
| Conceptual framework | Literature review | T 3.1 Visioning exercises with each TAELab | M12 | M24 | Maria Busse and Alma Moroder | ZALF (Germany) |
| Indicator framework | Interviews and participatory workshops | T 3.1 Visioning exercises with each TAELab | M9 | M12 | Maria Busse and Alma Moroder | ZALF (Germany) |
| Conceptual framework | Literature review | T 3.2. Mapping of existing agroecosystem and challenge definition | M9 | M24 | Tiffanie Stone | AU-Agroecology, (Denmark) |
| Indicator framework | Distributing participatory mapping materials | T 3.2. Mapping of existing agroecosystem and challenge definition | M13 | M16 | Tiffanie Stone | AU-Agroecology, (Denmark) |
| Indicator framework | Discussion about co-creation meeting in LL with mapping exercises | T 3.2. Mapping of existing agroecosystem and challenge definition | M16 | M18 | Tiffanie Stone | AU-Agroecology, (Denmark) |
| Conceptual framework | Literature review | T 3.3. Participatory assessment of landscape management in the territory surrounding LLs | M12 | M24 | José Luis Vicente Vicente | IEGD-CSIC (Spain) |
| Indicator framework | Interviews | T 3.3. Participatory assessment of landscape management in the territory surrounding LLs | M12 | M24 | José Luis Vicente Vicente | IEGD-CSIC (Spain) |

| WP 4 | Research Task/Analysis name | Task (T)/Topic | Start Date month (M) | End Date month (M) | Principal Investigator (s) | Organizing Institution |
| --- | --- | --- | --- | --- | --- | --- |
| Conceptual framework | Literature review | T 4.1. Business models & collective and self-organizational dimensions for AE transition | M10 | M16 | Daniel López | IEGD-CSIC (Spain) |
| Indicator framework | CANVAS assessment | T 4.1. Business models & collective and self-organizational dimensions for AE transition | M10 | M24 | Daniel López | IEGD-CSIC (Spain) |
| Conceptual framework | Literature review | T.4.2. Landscapes and foodscapes: assemblages between food production and circulation, socio-economic actors and territories | M12 | M24 | Jamila Haider and Courtney Adamson | SU-SRC (Sweden) |
| Indicator framework | Interviews | T.4.2. Landscapes and foodscapes: assemblages between food production and circulation, socio-economic actors and territories | M12 | M30 | Jamila Haider and Courtney Adamson | SU-SRC (Sweden) |
| Conceptual framework | Literature review | 4.3. Policies, territories, and people: multi-level assessment of policy coherence | M13 | M24 | Soledad Cuevas | IEGD-CSIC (Spain) |
| Indicator framework | Interviews on policy inventory | 4.3. Policies, territories, and people: multi-level assessment of policy coherence | M13 | M14 | Soledad Cuevas | IEGD-CSIC (Spain) |
| Indicator framework | Workshop on policy coherence matrix | 4.3. Policies, territories, and people: multi-level assessment of policy coherence | M16 | M17 | Soledad Cuevas | IEGD-CSIC (Spain) |
| Indicator framework | Workshop on analysis of a specific governance area based on the coherence analysis | 4.3. Policies, territories, and people: multi-level assessment of policy coherence | M20 | M22 | Soledad Cuevas | IEGD-CSIC (Spain) |

| WP 5 | Research Task/Analysis name | Task (T)/Topic | Start Date month (M) | End Date month (M) | Principal Investigator (s) | Organizing Institution |
| --- | --- | --- | --- | --- | --- | --- |
| Conceptual framework | Literature review | T 5.1. Capacity development on territorialized agroecological policies | M24 | M26 | Soledad Cuevas | IEGD-CSIC (Spain) |
| Indicator framework | Results sharing and debate | T 5.1. Capacity development on territorialized agroecological policies | M24 | M30 | Soledad Cuevas | IEGD-CSIC (Spain) |
| Indicator framework | Input into summary document | T 5.1. Capacity development on territorialized agroecological policies | M24 | M30 | Soledad Cuevas | IEGD-CSIC (Spain) |
| Indicator framework | Meeting with policymakers and civil society organisations | T 5.1. Capacity development on territorialized agroecological policies | M24 | M30 | Soledad Cuevas | IEGD-CSIC (Spain) |
| Conceptual framework | Literature review | T 5.2. Exploration of AKIS potential for agroecological socio-technical environments | M4 | M24 | Luca Colombo | FIRAB (Italy) |
| Indicator framework | Survey interest in and familiarity with AKIS | T 5.2. Exploration of AKIS potential for agroecological socio-technical environments | M15 | M16 | Luca Colombo | FIRAB (Italy) |
| Indicator framework | Preparation of the AKIS factsheet | T 5.2. Exploration of AKIS potential for agroecological socio-technical environments | M15 | M16 | Luca Colombo | FIRAB (Italy) |
| Indicator framework | Disseminate and discuss the AKIS factsheet | T 5.2. Exploration of AKIS potential for agroecological socio-technical environments | M18 | M19 | Luca Colombo | FIRAB (Italy) |
| Indicator framework | Selected open interviews with the LL members on AKIS | T 5.2. Exploration of AKIS potential for agroecological socio-technical environments | M18 | M20 | Luca Colombo | FIRAB (Italy) |
| Indicator framework | Workshop in the LL to capitalise information and possibly build a LL legacy making use of AKIS tools and opportunities | T 5.2. Exploration of AKIS potential for agroecological socio-technical environments | M20 | M26 | Luca Colombo | FIRAB (Italy) |
| Indicator framework | Report on AKIS dynamics and perspectives in the LL | T 5.2. Exploration of AKIS potential for agroecological socio-technical environments | M26 | M27 | Luca Colombo | FIRAB (Italy) |
| Indicator framework | Development of the knowledge system and role of actors in co-research/innovation | T 5.2. Exploration of AKIS potential for agroecological socio-technical environments | M18 | M20 | Luca Colombo | FIRAB (Italy) |
| Indicator framework | Identification of potentially relevant AKIS aspects to be further explored in the LL | T 5.2. Exploration of AKIS potential for agroecological socio-technical environments | M28 | M30 | Luca Colombo | FIRAB (Italy) |
| Indicator framework | Interest on possible AKIS initiatives building on TAELABS as LL follow up | T 5.2. Exploration of AKIS potential for agroecological socio-technical environments | M30 | M33 | Luca Colombo | FIRAB (Italy) |
| Indicator framework | Possible preparation of follow proposal | T 5.2. Exploration of AKIS potential for agroecological socio-technical environments | M28 | M36 | Luca Colombo | FIRAB (Italy) |
| Conceptual framework | Literature review | T 5.3. Innovative governance for territorial agroecological living labs and interface with European initiatives | M24 | M26 | Tiffanie Stone | AU-Agroecology (Denmark) |
| Indicator framework | Data analysis | T 5.3. Innovative governance for territorial agroecological living labs and interface with European initiatives | M24 | M30 | Tiffanie Stone | AU-Agroecology (Denmark) |

| WP 6 | Research Task/Analysis name | Task (T)/Topic | Start Date month (M) | End Date month (M) | Principal Investigator (s) | Organizing Institution |
| --- | --- | --- | --- | --- | --- | --- |
| Indicator framework | Project activities, outputs, outcomes, and impact | T 6.1 Project administration | M3 | M36 | Daniel López and Michela Pirredda | IEGD-CSIC, (Spain) |
| Indicator framework | Input into summary document, project activities, outputs, outcomes, and impact | Task 6.2 Communication, Dissemination and Exploitation Plan Management | M24 | M36 | Daniel López and Michela Pirredda | IEGD-CSIC, (Spain) |
| Indicator framework | Input into summary document | Task 6.3 Risk management and maximizing impacts | M33 | M36 | Daniel López and Michela Pirredda | IEGD-CSIC, (Spain) |
| Indicator framework | Input into summary document | Task 6.4 Data management plan | M6 | M36 | Daniel López and Michela Pirredda | IEGD-CSIC, (Spain) |

The following table (Table 4) shows the information relating to the description of the expected data type, the contact person and data access.

Table 4: Data used/gathered during the research mission period.

| Task | Data description (e.g., expedition, measuring device, sample, method, analysis, model, survey, ...) | Data generated and type | Responsible person | Internal data availability (planned due date) & location | Data format and number of files | Data publication |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Planned due date | Planned Repository (label, licensing, embargos) |
| T1.1 | Interviews | Interview transcripts + recordings | José Luis Vicente Vicente | 05/26 – SACO | Pseudomised transcripts (word) + consent signed | 12/26 | Digital.CSIC |
| T1.2 | Interviews and participatory workshops | Interview transcripts + recordings | Corrado Ciaccia | 12/27 – SACO | Pseudomised transcripts (word) + consent signed | 04/28 | Digital.CSIC |
| T2.1 | Interviews | Interview transcripts + recordings | Maria Busse /Alma Moroder | 04/26 – SACO | Pseudomised transcripts (word) + consent signed | 09/26 | Digital.CSIC |
| T2.2 | Literature review | Bibliography | Daniel López | 04/28 – SACO | Excel | 09/28 | Digital.CSIC |
| T3.1 | Interviews and participatory workshops | Interview transcripts + recordings | Maria Busse /Alma Moroder | 05/27 – SACO | Pseudomised transcripts (word) + consent signed | 09/27 | Digital.CSIC |
| T3.2 | Literature review | Bibliography and Interview transcripts + recordings | Tiffanie Stone | 05/27 – SACO | Excel and pseudomised transcripts (word) + consent signed | 09/27 | Digital.CSIC |
| T3.3 | Literature review and interviews | Bibliography and Interview transcripts + recordings | José Luis Vicente Vicente | 05/27 – SACO | Excel and pseudomised transcripts (word) + consent signed | 09/27 | Digital.CSIC |
| T4.1 | Literature review and participatory workshops | Bibliography and CANVAS assessment | Daniel López | 05/27 – SACO | Excel | 09/27 | Digital.CSIC |
| T4.2 | Literature review and interviews | Bibliography and Interview transcripts + recordings | Jamila Haider and Courtney Adamson | 12/26 – SACO | Excel and pseudomised transcripts (word) + consent signed | 03/27 | Digital.CSIC |
| T4.3 | Literature review, interviews and participatory workshops | Bibliography and Interview transcripts + recordings | Soledad Cuevas | 05/27 – SACO | Excel and pseudomised transcripts (word) + consent signed | 09/27 | Digital.CSIC |
| T5.1 | Literature review and meetings | Bibliography and recordings | Soledad Cuevas | 04/28 – SACO | Excel and pseudomised transcripts (word) + consent signed | 12/28 | Digital.CSIC |
| T5.2 | Literature review, interviews, seminars and workshops | Bibliography and Interview transcripts + recordings | Luca Colombo | 04/28 – SACO | Excel and pseudomised transcripts (word) + consent signed | 12/28 | Digital.CSIC |
| T5.3 | Literature review and data analysis | Bibliography and outcomes | Tiffanie Stone | 04/28 – SACO | Excel, Word, PDF,JPG, etc. | 12/28 | Digital.CSIC |
| T6.1 | Project administration | Project activities, outputs, outcomes, and impact | Daniel López and Michela Pirredda | 05/28 – SACO | Excel, Word, PDF | 05/28 | Digital.CSIC |
| T6.2 | Web page management, congress and seminars participation, Data Management Plan | Input into summary document, project activities, outputs, outcomes, and impact | Daniel López and Michela Pirredda | 05/28 – SACO | Excel, Word, PDF, web page, posters | 05/28 | Digital.CSIC |
| T6.3 | Risk management and maximizing impacts | Input into summary document | Daniel López and Michela Pirredda | 05/28 – SACO | Excel, Word, PDF | 05/28 | Digital.CSIC |
| T6.4 | Data management plan | Input into summary document | Daniel López and Michela Pirredda | 05/28 – SACO | Excel, Word, PDF | 05/28 | Digital.CSIC |

Table 5: TAELabs attachment concerning basics / Organizational aspects for data handling.

| Data collection | - Data formats and software are used that allow data exchange and long-term data use within the consortia, and later also with external users. - Statistical analyses for WP3.3 are carried out using R. - Data collections from surveys are stored as Excel files. - Answers of participatory workshops and interviews are saved as video recordings and are subsequently transcribed. The evaluation of the answers will be done using Atlas.ti or a similar program. |
| --- | --- |
| Data storage and backup | - During the project period, the data is stored on the infrastructures of the participating research institutions and backups will be created every three months by each responsible person (see previous table) and stored in the medium used to collect and analyse the data (either institutional computer or server). - Every six months, the data will be transferred to the institutional CSIC server - SACO - Only authorised employees/team members have access. - File names must include a specification of when data was collected and assigned the label: FT and data type. Example: 2023.03.21.FT.V2.InterviewTranscript. |
| Data documentation | Once data has been collected and analysed, as well as agreed by project members and data owners to be made publicly available, a metadata README file will be developed and stored in the shared SACO folder. Alternatively, this information can be given in the DMP and updated regularly. The DMP is available for all members via the internal shared SACO folder. |
| Data exchange | Data exchange is ensured within the consortium and across the consortia already before final data publication through the internal shared SACO folder. Data will be transferred for its archival in the long term via the institutional server SACO. |
| Usage rights | The members/collaborators who collect data within the framework of the TAELabs project have full rights over their member dataset, including the data they contribute to the TAELabs dataset and any other data they collect. If a member wants to publish from the developed datasets and it does not affect the following already established publications, they can do so by asking consortium members involved in collecting and generating the data and the Coordination team. The data will be stored securely on the Spanish National Research Council (CSIC) servers or on the computer of the IP address holder (using a personal and confidential access code) and processed with the utmost respect for the privacy of the participants. Compliance with current data protection regulations will be ensured, particularly with regard to the General Data Protection Regulation (GDPR) (Regulation (EU) 2016/679) of the European Parliament and of the Council of 27 April 2016, regarding the protection of natural persons with regard to the processing of personal data, and the free movement of such data. |